## Gantt
Task | Owner | Start | End | Status | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25
Phase 1 – Research & Setup
Read project manual & syllabus | All | 2026-09-07 | 2026-09-13 | Done
Shared folder + GitHub repo setup | Max | 2026-09-07 | 2026-09-13 | Done
Brainstorm UX / what to apply parallax to | Justin, Rotem | 2026-09-14 | 2026-09-27 | Done
Research face & eye tracking libraries | Tudor, Max | 2026-09-14 | 2026-09-20 | Done
Research Tauri + webview parallax rendering | Federico | 2026-09-14 | 2026-09-20 | Done
Research build systems, CI/CD, parallax math | Sotiris | 2026-09-14 | 2026-09-20 | Done
MediaPipe Face Mesh setup | Tudor | 2026-09-14 | 2026-09-27 | Done
C++/OpenCV eye-tracking comparison demo | Max | 2026-09-21 | 2026-10-04 | Done
3D scene v1 in Blender | Justin, Rotem | 2026-09-28 | 2026-10-11 | Done
Window system with lazy loading + controls overlay | Federico | 2026-09-28 | 2026-10-11 | Done
Face-tracking controller API for frontend | Tudor | 2026-09-28 | 2026-10-11 | Done
Face tracking → parallax mapping prototype | Sotiris | 2026-09-28 | 2026-10-11 | In progress
Skill class assignment | Max, Tudor | 2026-09-28 | 2026-10-11 | In progress
Phase 1 overview + project plan | Max | 2026-10-05 | 2026-10-11 | In progress
◆ Phase 1 deadline | — | 2026-10-11 | 2026-10-11 | Milestone
Phase 2 – Core Implementation
Python ↔ Tauri bridge for tracking data | Federico, Tudor | 2026-10-12 | 2026-10-25 | Not started
Render parallax with the Blender scenes in Tauri | Federico | 2026-10-12 | 2026-11-08 | Not started
Fix 3D model issues, camera placements, colours | Justin, Rotem | 2026-10-12 | 2026-10-25 | Not started
UI for mode selection (HTML/TypeScript) | Rotem | 2026-10-12 | 2026-11-01 | Not started
Tracking performance optimisation (≥30 FPS) | Sotiris, Tudor | 2026-10-19 | 2026-11-08 | Not started
Calibration + sensitivity settings | Justin, Sotiris | 2026-10-26 | 2026-11-15 | Not started
Extra scenes (artwork parallax, more 3D scenes) | Justin, Rotem | 2026-10-26 | 2026-11-22 | Not started
User-uploaded image mode | Federico, Rotem | 2026-11-02 | 2026-11-22 | Not started
CI/CD pipeline (build + test on commit) | Sotiris | 2026-10-12 | 2026-10-25 | Not started
Eye-tracking accuracy improvements | Tudor, Max | 2026-11-02 | 2026-11-22 | Not started
Phase 2 report + presentation | Max, Justin | 2026-11-16 | 2026-11-29 | Not started
◆ Phase 2 deadline | — | 2026-11-29 | 2026-11-29 | Milestone
Phase 3 – Testing, Polish & Delivery
User testing (≥5 participants, feedback form) | Justin, Max | 2026-11-30 | 2026-12-20 | Not started
Performance profiling + optimisation | Sotiris, Tudor | 2026-11-30 | 2026-12-20 | Not started
UI / UX polish | Federico, Rotem | 2026-11-30 | 2026-12-20 | Not started
Web hosting for examiners | Sotiris | 2026-12-07 | 2026-12-20 | Not started
Christmas break | — | 2026-12-21 | 2027-01-03 | Break
Bug fixing + code freeze | Federico, Sotiris | 2027-01-04 | 2027-01-17 | Not started
Final report | Max, Justin | 2027-01-04 | 2027-01-24 | Not started
Final presentation + demo prep | Rotem, Tudor | 2027-01-11 | 2027-01-31 | Not started
◆ Final deadline | — | 2027-01-31 | 2027-01-31 | Milestone
Note on A1: Phase dates after Phase 1 are assumptions – adjust to the official course deadlines. Bars are static colours so they show in Google Sheets too — recolour cells if dates change.

## Summary
Status overview
Status | Tasks
Done | 11
In progress | 3
Not started | 18
Blocked | 0
Milestone | 3
Total tasks | 32
% done | 34.38%
Legend
Done
In progress
Not started
Blocked
Milestone
Break
Current week
Bars are filled cells (not formulas) so they render in Google Sheets / Numbers. Dates after Oct 11 2026 are estimates.